# SkaFld Trailhead

ESUSD Partnership Implementation Plan

Prepared By:  SkaFld Studio LLC

Prepared For:  El Segundo Unified School District

Contact:  Charles Sims — charles@skafldstudio.com

Date:  March 2026

## Overview

SkaFld Trailhead is a portfolio-based career pathway program where high school students build employer-validated portfolios by solving real problems for local companies using AI. Students develop durable metacognitive skills — decomposition thinking, cross-domain pattern recognition, and responsible AI practices — that transfer across any tool or domain.

This plan outlines the implementation partnership between SkaFld Studio LLC and El Segundo Unified School District to pilot SkaFld Trailhead with 12 students over 12 months.

### Program at a Glance

| ELEMENT | DETAIL |
| --- | --- |
| Students | 12 in 1 cross-grade team (9th-12th) |
| Teacher Mentor | 1 dedicated teacher mentor |
| Session Format | Weekly 90-minute sessions |
| Employer Partners | 2-3 local companies (aerospace, tech) |
| Curriculum | SkaFld Ideation Methodology |
| Platform | SkaFld Trailhead (AI-powered, COPPA/FERPA compliant) |
| Duration | 12 months |

## Responsibility Matrix

What SkaFld Provides

- SkaFld Trailhead Platform — AI Coaching Engine, Portfolio Review System, Student Progression Tracking, Teacher Dashboard. Fully COPPA/FERPA compliant with enterprise SSO (Microsoft/Google).

- Curriculum & Training — Complete SkaFld Ideation Methodology curriculum for weekly 90-minute sessions. Teacher mentor training and ongoing support.

- Employer Partnerships — Recruitment and onboarding of 2-3 employer partners in El Segundo's aerospace/tech corridor for project briefs and portfolio review.

- Program Management — Day-to-day coordination, progress tracking, employer communications, quarterly portfolio review facilitation.

- Assessment & Reporting — Learning outcome tracking with disaggregated equity monitoring. Progress reports and year-end assessment.

What ESUSD Provides

- District Point of Contact — A designated coordinator (CTE coordinator, assistant principal, or equivalent) to serve as the primary liaison between SkaFld and the district.

- Facility Access — A classroom or meeting space for weekly 90-minute sessions (after school or embedded in CTE block, TBD).

- Teacher Mentor — 1 teacher mentor to facilitate team sessions. SkaFld provides all training and curriculum materials; the teacher brings their knowledge of students and school culture.

- Student Recruitment Support — Help promoting the program to students and families, processing parental consent forms, and supporting equitable recruitment (targeting 50% female, 40% FRL, 30% first-generation).

- Administrative Support — Standard district approvals, data sharing agreements, and coordination with existing CTE or after-school programming.

## Implementation Timeline

Phase 1: Foundation (Months 1-3)

| MONTH | SKAFLD ACTIONS | ESUSD ACTIONS |
| --- | --- | --- |
| 1 | Complete SkaFld Trailhead platform buildout; begin employer partner recruitment | Designate district point of contact; identify facility for sessions |
| 2 | Finalize platform (AI Coaching Engine, Portfolio Review System, Teacher Dashboard); onboard first employer partners | Identify teacher mentor; begin internal communications about program |
| 3 | Platform ready for pilot; 2-3 employer partners signed; develop teacher training materials | Teacher mentor confirmed; facility reserved; student recruitment materials distributed |

Month 3 Milestones:

- SkaFld Trailhead platform ready for pilot

- 2-3 signed employer partner commitments

- Teacher mentor identified and scheduled for training

Phase 2: Launch (Months 4-6)

| MONTH | SKAFLD ACTIONS | ESUSD ACTIONS |
| --- | --- | --- |
| 4 | Conduct teacher mentor training; finalize student applications; configure platform for ESUSD SSO | Open student applications; support equitable recruitment; process parental consent forms |
| 5 | Form team of 12 students; assign employer project brief; launch weekly sessions | Students begin attending sessions; teacher mentor actively facilitating |
| 6 | First project cycle underway; mid-year progress report | Ongoing facility and schedule support; feedback on program integration |

Month 5 Milestone: Pilot launched — 12 students in 1 team

Month 6 Milestone: Mid-year progress report completed

Phase 3: Execution (Months 7-10)

| MONTH | SKAFLD ACTIONS | ESUSD ACTIONS |
| --- | --- | --- |
| 7-8 | First project deliverables completed and submitted to employers | Teacher mentor supports student presentations |
| 9 | First employer portfolio review panel — all 12 students receive employer feedback | Facilitate student participation in review panel |
| 10 | Second project cycle launched with new employer briefs | Continue session support; share early outcomes with district leadership |

Month 9 Milestone: First employer portfolio review cycle completed

Phase 4: Validation (Months 11-12)

| MONTH | SKAFLD ACTIONS | ESUSD ACTIONS |
| --- | --- | --- |
| 11 | Facilitate micro-internship placements (3+ students); second portfolio review | Support work-based learning logistics (permissions, scheduling) |
| 12 | Year-end assessment; outcomes report; Year 2 expansion planning | Joint review of outcomes; discuss Year 2 continuation and expansion |

Month 11 Milestone: 3+ micro-internship placements

Month 12 Milestone: Year-end report with outcomes and Year 2 plan

## Immediate Next Steps (April 2026)

| # | ACTION | OWNER | TARGET DATE |
| --- | --- | --- | --- |
| 1 | Schedule 30-minute partnership kickoff call | Charles Sims / Dr. Johnson | Week of April 13 |
| 2 | Designate ESUSD point of contact | Dr. Johnson | April 18 |
| 3 | Identify facility for weekly sessions | ESUSD Point of Contact | April 25 |
| 4 | Share teacher mentor criteria and identify candidate | SkaFld + ESUSD | May 2 |
| 5 | Execute data sharing / partnership agreement | Both parties | May 9 |

## Equity Commitments

SkaFld Trailhead is designed for equitable access. Recruitment and team formation will target:

- 50% female / 50% male participation

- 40% Free/Reduced Lunch eligible students

- 30% first-generation college-bound students

All platform features are built with accessibility in mind, and the cross-grade team model (12th graders mentoring 10th graders, 11th graders mentoring 9th graders) ensures peer support structures are embedded from day one.

## Key Contacts

SkaFld Studio LLC

| NAME | ROLE | EMAIL |
| --- | --- | --- |
| Charles Sims | Project Director | charles@skafldstudio.com |
| Keith Coleman | Strategy & Partnerships | keith@skafldstudio.com |
| Mike Belloli | Technology & Operations | mike@skafldstudio.com |
| Danielle Joseph | Chief of Staff | danielle@skafldstudio.com |

El Segundo Unified School District

| NAME | ROLE | EMAIL |
| --- | --- | --- |
| Dr. Jason Johnson | Superintendent | jjohnson@esusd.net |
| TBD | District Point of Contact | TBD |

SkaFld Studio LLC — 889 N Douglas St, Suite 201, El Segundo, CA 90245